# Third Avenue “One Stop Shop” Healthcare Tracker Charter

# Date: Sept. 10, 2025

| Project Title: TBD |  |  |  |
| --- | --- | --- | --- |
| Project Start Date: 9/18/25 Projected Finish Date: 1/19/26 |  |  |  |
| Key Schedule Milestones: - Working version released “well before” planned official release - Complete and deliver final product by January 19th |  |  |  |
| Budget Information: Third Avenue has allocated $350,000 towards the project although the entire scope is not completely defined. To dial in estimates management has had the programmers develop a complexity analysis for each major feature in the app, which in turn may help the estimating process later on in the project. |  |  |  |
| Project Manager: Bradley Moore, 586-922-7885, bradlmoo@umich.edu |  |  |  |
| Project Objectives: The objective of the project is to create a mobile app that helps Third Avenue find its corporate identity and establish a permanent footing. The project team aims to deliver a health care tracking app that will: - Appeal to a more universal market as opposed to the niche markets of the past. - Create a highly usable app to tend to the older target market. - Effectively monetize the app generating an acceptable ROI. - Produce working version of the application in 4 months. - Meet or beat the $350,000 budget allocation target. |  |  |  |
| Success Criteria: The project will be considered a success if the team delivers a working version of the app within the 4-month deadline and achieves or beats the budget set forth of $350,000. The app must be deemed usable relative to the target audience by management and have a written monetization plan. The app also must have a workable version developed well before planned official release |  |  |  |
| Approach: - By 9/25, identify personnel for the project and define roles within a Scrum development team. - By 10/9, work to more clearly define Scope, Timing, and Cost for project and create visual plan for the mobile app’s architecture. Using the programmer’s complexity analyses, a Product Backlog will be created in preparation for first sprint backlog development. - First Scrum sprint scheduled to begin 10/13 will last 4 weeks and will aim to produce a workable version of the app well before official release. - Second 4-week Scrum Sprint to begin 11/12 after first sprint review and retrospective. Incremental product deliverable will be available for review and Scope and Cost will be dialed in much more accurately. - The 3rd and final Sprint will be 3 weeks long, begin on 12/15, and will aim to resolve all remaining Product Backlog items. - The project allows for two weeks of “Technical Float”, with the third sprint concluding 1/5, during which the product can be tested and polished for the last time. Also, the team can work on the presentation of the software to project sponsors and stakeholders. The team will need to be highly cognizant of hours allocated to the project at this point to help maintain budget goals. Ideally this “technical period” lasts for 1 week and the team delivers the product early to project finish date by 1 week on 1/12 |  |  |  |
| Roles and Responsibilities |  |  |  |
| Name and Signature | Role | Position | Contact Information |
| Comments: (Handwritten or typed comments from above stakeholders, if applicable) |  |  |  |